# CompoundIQ Launch Kit

Working documents for the first 30 days of go-to-market execution. These are not investor-facing polished docs — they’re the templates and checklists you’ll actively use to lock in design partners and start generating revenue.

## Contents

| File | Purpose | When to Use |
| --- | --- | --- |
| clinic-outreach-email.md | Email templates for warm clinic introductions | Week 1 — send to 3-5 warm contacts |
| pharmacy-outreach-email.md | Email templates for compounding pharmacies | Week 2-3 — AFTER you have a committed clinic to name-drop |
| legitscript-application-checklist.md | Step-by-step LegitScript certification guide | Week 1 — submit in parallel; 2-4 week turnaround |
| design-partner-agreement.md | Non-binding Letter of Intent template | Week 1-2 — send after a clinic verbally commits |

## The Sequence

Week 1:  Clinic outreach (5-8 warm contacts)  +  LegitScript application submitted
         ↓
Week 2:  1-2 clinics verbally committed        → send Design Partner Agreement (LOI)
         ↓
Week 3:  Clinic LOI signed                     → pharmacy outreach with clinic name-drop
         ↓
Week 4:  Pharmacy catalog received             → load into app via /ops/catalog upload
         ↓
         First real prescription end-to-end    → your first $22.50 platform fee

## Key Principle

Clinic commitment unlocks everything downstream. Pharmacy outreach cold is weak. Pharmacy outreach with a committed clinic name attached converts at ~40% vs ~5% cold. Do not skip the order.

## Demo Materials (Already Exist)

Point clinics to:

- Live app: https://functional-medicine-infrastructure.vercel.app

- Demo walkthrough PDF: docs/POC-DEMO-DETAILED.pdf (25-page step-by-step)

- Quickstart PDF: docs/POC-DEMO-QUICKSTART.pdf (2-page cheat sheet)

- Demo credentials: See Section 17 of POC-DEMO-DETAILED

## Budget Estimate for Week 1

| Item | Cost |
| --- | --- |
| LegitScript application | $975 |
| LegitScript annual monitoring (pro-rated) | $0 until approved |
| Domain email setup (if needed) | $0–$15/mo |
| Clinic outreach | $0 (warm intros) |
| Pharmacy outreach | $0 (email only) |
| Total week-1 cash out | ~$1,000 |

Update this README as you hit each milestone.