# CompoundIQ Pre-Launch Checklist

Purpose: Track every non-product task that must be complete before the first real patient transaction can flow through the platform. The app works. The demo is tight. These are the business and operational bases that block actual revenue.

Owner: [YOUR NAME] Last updated: 2026-04-16 Target first-real-order date: [FILL IN]

## Status Dashboard

| Bucket | Items | Completed | In Progress | Not Started |
| --- | --- | --- | --- | --- |
| 1. Business & Legal | 8 | 0 | 0 | 8 |
| 2. Public Web Presence | 5 | 0 | 0 | 5 |
| 3. Production Readiness | 8 | 0 | 0 | 8 |
| 4. 60-Day Nice-to-Haves | 8 | 0 | 0 | 8 |
| Total | 29 | 0 | 0 | 29 |

Update this table as you work. At a glance you see how close you are to launch-ready.

## Critical Path — Order of Operations

These items block each other. Do them in this order:

- Entity + EIN + bank account (blocks everything financial)

- BAA request emails (take 1-2 weeks each — start immediately, finish later)

- Insurance quotes (LegitScript asks; some BAAs require)

- Marketing website + privacy/ToS (blocks LegitScript review, blocks credible outreach)

- Stripe Connect platform application (1-3 week approval window — start early)

- LegitScript application (2-4 week turnaround — use outputs from 1-4 above)

- Twilio A2P 10DLC registration (1-3 week carrier review — independent track)

- Documo production account (days, not weeks)

- Monitoring/alerting wired to real phone (30 minutes once Sentry/PagerDuty keys are in hand)

Everything else runs in parallel or is post-launch polish.

## Bucket 1: Business & Legal Foundation

These items block LegitScript, Stripe Connect platform approval, and any real money movement. Get them done first.

### 1.1 Form the Business Entity

- ☐ Status: Not started

- What: File as Delaware C-Corporation (recommended for future fundraising and standard SAFE/equity instruments). Alternative: LLC if staying solo indefinitely, but C-Corp is much easier to fundraise into.

- Why: Required for business banking, Stripe Connect platform, BAAs, and any investor/angel round. SAFEs specifically require a C-Corp.

- How: Use Stripe Atlas ($500), Clerky ($99 + filing fees), or a startup-specialized lawyer ($2-4K). Atlas is simplest for pre-revenue founders.

- Cost: $500-$4,000 depending on path

- Timeline: 5-10 business days

- Dependencies: None

- Deliverables: Certificate of Incorporation, Bylaws, Stock Purchase Agreement (founder shares), 83(b) election filed with IRS within 30 days of stock issuance

- Notes: ___

### 1.2 Obtain EIN (Employer Identification Number)

- ☐ Status: Not started

- What: Federal tax ID for the business. Apply on irs.gov.

- Why: Required for business bank account, Stripe, payroll (if any), all vendor BAAs.

- How: irs.gov → Apply for EIN Online. Takes 15 minutes, instant approval during business hours.

- Cost: Free

- Timeline: Same day (if within 7am-10pm ET)

- Dependencies: Entity formed (1.1)

- Deliverables: CP 575 confirmation letter (save PDF — you’ll need it 10+ times)

- Notes: ___

### 1.3 Open Business Bank Account

- ☐ Status: Not started

- What: Dedicated business checking + savings. Mercury and Brex are the startup standards.

- Why: Stripe Connect payouts, BAAs, and basic financial hygiene (never commingle personal and business funds — pierces the corporate veil).

- How: Mercury (mercury.com) or Brex (brex.com). Both are free and support online-only onboarding.

- Cost: $0 (free checking for startups)

- Timeline: 1-3 business days

- Dependencies: Entity + EIN (1.1, 1.2)

- Deliverables: Account number + routing number, debit card, online banking access

- Notes: Request a voided check PDF — needed for Stripe payout configuration

### 1.4 General Liability Insurance

- ☐ Status: Not started

- What: $1M liability coverage — industry standard minimum.

- Why: LegitScript asks. Some vendor BAAs require. Protects against slip-and-fall-style claims.

- How: Hiscox (hiscox.com), Next Insurance (nextinsurance.com), or Chubb. Online quote in 10 minutes.

- Cost: $500-$1,500/year for pre-revenue tech startup

- Timeline: Same day quote; binder same day; policy 1-3 days

- Dependencies: Entity (1.1)

- Deliverables: Certificate of Insurance (COI) PDF — attach to LegitScript app

- Notes: ___

### 1.5 Cyber Liability Insurance

- ☐ Status: Not started

- What: Coverage for data breaches, ransomware, PHI incidents.

- Why: Strongly recommended for any HealthTech touching PHI. Required by some enterprise clinic partners in future contracts.

- How: Coalition (coalitioninc.com), Resilience (resilience.com), or Beazley. Coalition is startup-friendly.

- Cost: $1,500-$5,000/year

- Timeline: 1-2 weeks (they’ll ask security questions)

- Dependencies: Entity (1.1), basic security posture documentation (link to docs/technical/security-audit from archive)

- Deliverables: Policy PDF

- Notes: Ask about “waiting period” and “retroactive coverage” — both matter for HIPAA

### 1.6 BAA Requests — Send in Parallel, All 6 Today

Send email requests TODAY so BAAs land by the time LegitScript asks. Each vendor has a specific process:

- ☐ Supabase BAA — Email security@supabase.com. Requires Team plan ($599/mo) or Enterprise. Timeline: 3-5 business days.

- ☐ Stripe BAA — Dashboard → Settings → Business details → Request HIPAA BAA. Timeline: 5-10 business days.

- ☐ Twilio BAA — https://www.twilio.com/docs/glossary/what-is-hipaa → contact sales. Requires paid account. Timeline: 5-10 business days.

- ☐ Documo BAA — Email support@documo.com. Included on their HIPAA-eligible plan. Timeline: 2-5 business days.

- ☐ Vercel BAA — Requires Enterprise plan. Email sales@vercel.com. Timeline: 7-14 business days. This is the most likely bottleneck.

- ☐ Sentry BAA — Business plan or higher. Email compliance@sentry.io. Timeline: 3-7 business days.

Cost: Most BAAs require paid/enterprise tiers. Budget ~$800-$1,500/mo additional across all 6 vendors once BAAs are in place.

Notes: ___

### 1.7 Founder Stock Issuance + 83(b) Election

- ☐ Status: Not started

- What: Issue yourself founder shares (typically 8-10M shares at $0.0001/share) and file 83(b) election with IRS within 30 days.

- Why: Locks in cheap tax basis. Miss the 30-day window and you can owe huge taxes later as the company appreciates.

- How: Stripe Atlas / Clerky handles this automatically. If you used a lawyer, they should have handled it. If you formed your own entity manually, file 83(b) immediately.

- Cost: Included in entity formation services

- Timeline: Must file 83(b) within 30 days of stock purchase — NO EXCEPTIONS

- Dependencies: Entity formed (1.1)

- Deliverables: Stock certificate, 83(b) election mailed certified to IRS, copy kept in company records

- Notes: This is the single easiest way to lose tens of thousands of dollars to the IRS. Don’t skip or delay.

### 1.8 Accounting Software + Bookkeeper

- ☐ Status: Not started

- What: QuickBooks Online ($30/mo) or Xero ($15/mo), or Bench.co ($249/mo for managed bookkeeping).

- Why: Investors will ask for books. LegitScript doesn’t require it, but you’ll need monthly financials by the time you raise.

- How: Pick one, connect bank account + Stripe, chart of accounts pre-built for SaaS.

- Cost: $15-$249/mo

- Timeline: 1 hour setup

- Dependencies: Bank account (1.3)

- Notes: Bench.co is worth it if you hate bookkeeping. QBO if you want to DIY.

## Bucket 2: Public Web Presence

When a clinic or pharmacy Googles “CompoundIQ” after getting your cold email, they should find a legitimate business — not a Vercel default page or nothing at all. This is the highest-leverage item in the whole checklist.

### 2.1 Marketing Website

- ☐ Status: Not started

- What: A 1-3 page professional marketing site at compoundiq.com (or whatever domain you pick).

- Required pages:

  - Home: 3-sentence pitch, 2-3 product screenshots, “Request a Demo” button

  - How It Works: the 3-tier flow (clinic → patient → pharmacy)

  - About: team + contact info (email + phone)

  - Privacy Policy (see 2.3)

  - Terms of Service (see 2.4)

- Why: LegitScript requires a live professional site. Cold outreach conversion drops ~50% without one. Design partner clinics do due diligence.

- How: Three options:

  - Framer (framer.com) — drag-and-drop, 1-2 weekend hours, ~$20/mo

  - Webflow — more powerful but steeper learning curve, ~$18/mo

  - Next.js landing page — matches existing stack, more work but more control

- Cost: $15-$20/mo + domain

- Timeline: 1-2 weekends

- Dependencies: Domain (2.2)

- Notes: ___

### 2.2 Domain Name + Professional Email

- ☐ Status: Not started

- What: Register compoundiq.com (if available) or alternate. Set up Google Workspace for professional email.

- Why: @compoundiq.com converts 3-5× better than @gmail.com on cold outreach. LegitScript expects a professional domain.

- How:

  - Domain: Namecheap or Cloudflare Registrar (cheaper than GoDaddy)

  - Email: Google Workspace Business Starter ($6/mo/user)

- Cost: ~$12/year domain + $6/mo/user email

- Timeline: 1 hour total

- Dependencies: None

- Notes: Also set up founders@, support@, legal@, security@ aliases that all forward to you. Partners check these.

### 2.3 Privacy Policy

- ☐ Status: Not started

- What: HIPAA-compliant privacy policy covering PHI handling.

- Why: LegitScript, clinic LOIs, BAA counterparties all ask.

- How:

  - DIY with Termly (termly.io) — generate in 15 min, ~$10/mo

  - Iubenda (iubenda.com) — similar

  - Lawyer-drafted — $500-$2,000 one-time

  - Reference: our existing docs/archive/source/technical/security-audit.md has much of the substance

- Cost: $10/mo (tool) or $500-$2,000 (lawyer)

- Timeline: 30 min (tool) or 1 week (lawyer)

- Dependencies: Marketing site to host it on

- Notes: ___

### 2.4 Terms of Service

- ☐ Status: Not started

- What: Terms of use for the platform.

- Why: Required for LegitScript. Required in every clinic LOI. Required for Stripe Connect platform application.

- How: Same tools as 2.3. Reference our existing platform architecture when specifying limitations of liability (we are infrastructure, not a pharmacy, not a prescriber).

- Cost: Included with 2.3

- Timeline: Included with 2.3

- Dependencies: 2.3

- Notes: ___

### 2.5 Public Contact Methods

- ☐ Status: Not started

- What: Real phone number + physical address on the site.

- Why: LegitScript verifies these. Clinics expect them. “Contact us” forms alone don’t count.

- How:

  - Phone: Google Voice (free) or OpenPhone ($15/mo) forwarding to your mobile

  - Address: Virtual office (Regus, iPostal1) ~$10-30/mo OR your home address if comfortable

- Cost: $0-$45/mo

- Timeline: Same day

- Notes: Don’t use a PO Box — most B2B counterparties reject those.

## Bucket 3: Production Readiness

Items required before the first real prescription can flow through the platform with a real patient paying a real pharmacy.

### 3.1 Stripe Connect Platform Application

- ☐ Status: Not started

- What: Apply to be a Stripe Connect Express platform (not just a standard merchant).

- Why: Required to move money between patients, platform, and clinic payouts. Different (stricter) review process than a standard Stripe account.

- How: Stripe dashboard → Connect → Apply to be a platform. Requires detailed business description, website, expected volume, KYC documentation.

- Cost: Free; standard Stripe processing fees (2.9% + $0.30) apply

- Timeline: 1-3 weeks (sometimes faster)

- Dependencies: Entity (1.1), EIN (1.2), bank account (1.3), marketing site (2.1), BAA requested (1.6)

- Notes: Write the business description carefully. Emphasize: you are a B2B2C infrastructure platform, you do not handle prescriptions, you move payment only.

### 3.2 Twilio A2P 10DLC Registration

- ☐ Status: Not started

- What: Register your brand + SMS campaign with US mobile carriers (mandatory since 2023 for all A2P messaging).

- Why: Without registration, your SMS checkout links will be throttled or blocked by carriers. Patients won’t get the text.

- How: Twilio dashboard → Messaging → Compliance → A2P 10DLC. Brand registration ($44 one-time), campaign registration ($10/mo per campaign).

- Cost: ~$54 first year, $10/mo ongoing

- Timeline: 1-3 weeks (TCR review is slow)

- Dependencies: Entity (1.1), professional email domain (2.2), HIPAA BAA (1.6) if messaging contains PHI

- Notes: Our current SMS contains only first name + URL — no PHI. Still needs registration.

### 3.3 Documo Production Account + Dedicated Fax Number

- ☐ Status: Not started

- What: Upgrade Documo to production tier with HIPAA BAA, provision a dedicated outbound fax number.

- Why: Current setup is test-tier. Real pharmacy submissions need a real fax number + HIPAA coverage.

- How: Documo dashboard → Upgrade plan → Request BAA + fax number provisioning.

- Cost: $30-$150/mo depending on volume tier

- Timeline: 1-3 business days

- Dependencies: BAA (1.6)

- Notes: ___

### 3.4 LegitScript Certification

- ☐ Status: Not started

- What: Healthcare Merchant certification.

- Why: Required to run healthcare-adjacent Google/Meta ads, expected by clinics and pharmacies during due diligence, sometimes required by Stripe for healthcare merchants.

- How: Full checklist in legitscript-application-checklist.md — follow that doc step-by-step.

- Cost: $975 application + $1,295/year monitoring

- Timeline: 2-4 weeks from complete submission

- Dependencies: Entity, EIN, insurance, BAAs, marketing site, privacy policy, ToS (1.1–2.4)

- Notes: Everything else in Bucket 1 and 2 must be done first.

### 3.5 Monitoring + Alerting Wired to a Real Phone

- ☐ Status: Not started

- What: Sentry alerting + PagerDuty (or Opsgenie) configured to actually page someone when critical errors or cron failures occur.

- Why: Right now errors silently log. In production, a cron failure at 2am must wake someone up.

- How:

  - Sentry: configure Issue Alerts for high-severity errors to fire Slack + PagerDuty

  - PagerDuty: free tier covers 5 users; set up on-call schedule (just you to start)

  - Test end-to-end: trigger a fake error and confirm your phone actually buzzes

- Cost: Free tier works until ~5 responders

- Timeline: 2-4 hours setup + 30 min end-to-end test

- Dependencies: None

- Notes: CLAUDE.md already references PagerDuty routing key. Confirm it’s wired to a real account.

### 3.6 Supabase Point-in-Time Recovery + Scheduled Backups

- ☐ Status: Not started

- What: Enable PITR in Supabase project settings.

- Why: If the database is corrupted or a bad migration runs, PITR lets you rewind to any point in the last 7 days. Without it, you have only daily snapshots.

- How: Supabase dashboard → Database → Backups → Enable Point-in-Time Recovery. Requires Team plan ($599/mo).

- Cost: Included in Team plan (which you need for BAA anyway)

- Timeline: 1 click

- Dependencies: Team plan subscription (part of 1.6 BAA upgrade)

- Notes: Also configure Weekly Physical Backups if available.

### 3.7 Support Inbox + Response Process

- ☐ Status: Not started

- What: support@compoundiq.com email with a defined response SLA (e.g. 4 business hours for design partners).

- Why: When a design partner clinic emails needing help, it must land somewhere and get a reply fast.

- How:

  - Set up the alias to forward to you

  - For scale later: Front, Help Scout, or Zendesk (all have startup tiers ~$15-30/user/mo)

- Cost: $0 initially; $15-30/user/mo at scale

- Timeline: 15 min setup

- Dependencies: Professional email (2.2)

- Notes: Design Partner Agreement promises 2-hour response for critical issues — actually plan to honor this.

### 3.8 Mobile Device Validation

- ☐ Status: Not started

- What: End-to-end patient checkout flow tested on a real iPhone (Safari) and a real Android phone (Chrome). Clinic app and ops dashboard tested on iPad Safari and iPhone Safari for graceful degradation.

- Why: Patient checkout is mobile-first by design — patients receive SMS and tap the link on their phone. If Apple Pay / Google Pay doesn’t render correctly on real iOS Safari or Android Chrome, the first real transaction fails silently. Zero rounds of Cowork QA ran on mobile; this is the single highest-risk validation gap before first production order.

- How: Follow the full test plan in mobile-validation-test-plan.md — 30-minute execution with your phone + your wife’s phone, covers all 3 applications on 4 device/browser combinations.

- Cost: $0 (own devices) or ~$40/mo (BrowserStack / LambdaTest if no Android available)

- Timeline: 30-45 min first pass; re-run whenever frontend changes ship to /checkout/* or any mobile-responsive component

- Dependencies: Live deployment (already met)

- Notes: Patient checkout is the blocking gate. Clinic app and ops dashboard failures on mobile are logged as Priority 2 bugs, not launch blockers.

## Bucket 4: 60-Day Nice-to-Haves

Worth doing within 2 months of first real order. Not blockers, but high-leverage.

### 4.1 Status Page

- ☐ Status: Not started

- What: Public-facing status page showing platform uptime by component.

- Why: Pharmacy partners and clinics will ask. Enterprises expect it.

- How: statuspage.io (Atlassian, $0-$79/mo), Instatus (free tier), or self-hosted with Upptime (free GitHub-based).

- Cost: $0-$79/mo

- Timeline: 2-4 hours

- Notes: ___

### 4.2 Recorded Demo Video

- ☐ Status: Not started

- What: 5-8 minute Loom walking through the clinic workflow + patient checkout.

- Why: For clinics who can’t take a live meeting. Embeds in emails and the marketing site.

- How: Loom (loom.com, free tier works). Follow POC-DEMO-QUICKSTART for a tight 5-minute version.

- Cost: $0 (free tier) or $15/mo (Pro)

- Timeline: 2-3 hours with retakes

- Notes: Keep it under 8 minutes. Longer videos don’t get watched.

### 4.3 CRM (Customer Relationship Management)

- ☐ Status: Not started

- What: Track every clinic and pharmacy in your pipeline with contact history, next action, and status.

- Why: By the time you have 15 clinic leads, you’ll lose track without one.

- How: HubSpot Free, Pipedrive ($14/user/mo), Attio (modern alternative, $29/user/mo), or even a well-structured Airtable/Notion base.

- Cost: $0-$29/user/mo

- Timeline: 1-2 hours setup

- Notes: HubSpot Free is plenty for <100 contacts.

### 4.4 Advisory Board (Informal)

- ☐ Status: Not started

- What: 2-3 advisors who can make intros + give advice in exchange for 0.25-0.5% common stock each (2-year vest).

- Why: Credibility signal for investors. Warm intros to clinics and pharmacies.

- How: Identify 3-5 targets (functional medicine thought leaders, pharmacy operators, healthcare exits). Offer FAST (“Founder Advisor Standard Template” by Founder Institute — free standard doc).

- Cost: ~0.75-1.5% total equity pool; legal costs to paper the FAST agreements ~$500

- Timeline: 1-2 months to close 2-3 advisors

- Notes: Don’t give equity until they’ve actually helped (intro made, meeting taken). Lagging advisors with equity is the #1 cap table regret.

### 4.5 Design Partner Case Study Plan

- ☐ Status: Not started

- What: Written case study with 1-2 design partners after 60-90 days of real use.

- Why: Most important marketing asset for next wave of clinic outreach.

- How: Interview → draft → clinic approves → publish on marketing site + pitch deck.

- Cost: $0

- Timeline: 2 weeks from first interview

- Dependencies: At least one design partner with 30+ days of real usage

- Notes: ___

### 4.6 TCPA Compliance for SMS

- ☐ Status: Not started

- What: Documented opt-in flow + opt-out handling for all patient SMS.

- Why: TCPA violations = $500-$1,500 per message statutory damages. Trial lawyers scan for this.

- How:

  - Opt-in: captured during patient record creation in the clinic app (store timestamp + source)

  - Opt-out: “Reply STOP to opt out” in every message; honor within 10 min

  - Compliance doc: short internal memo documenting the process

- Cost: $0

- Timeline: 2-4 hours of work

- Dependencies: Twilio A2P 10DLC (3.2)

- Notes: Check src/lib for existing opt-out handling — we may already have this.

### 4.7 Data Retention + Deletion Policy

- ☐ Status: Not started

- What: Written policy for how long PHI is retained and how deletion requests are handled.

- Why: HIPAA requires it. Clinic BAAs will reference it. Patients in some states (CA via CMIA, many others) can request deletion.

- How: Short internal policy doc. Reference our existing soft-delete pattern (all tables have deleted_at) and order_status_history immutable audit.

- Cost: $0 (DIY) or $500 (lawyer-reviewed)

- Timeline: 2-4 hours

- Notes: ___

### 4.8 Founder Employment Agreement + IP Assignment

- ☐ Status: Not started

- What: Employment agreement between you and the company, with IP assignment clause ensuring all code/IP you’ve written belongs to the C-Corp.

- Why: Without this, investors will refuse to fund. Any IP that predates the IP assignment is ambiguous.

- How: Stripe Atlas includes this. Lawyer can paper it for $500-1K. Clerky also includes.

- Cost: Usually included in entity formation package

- Timeline: 1 hour to review and sign

- Dependencies: Entity (1.1)

- Notes: Date the IP assignment as early as possible — ideally the same day as incorporation.

## Suggested 4-Week Sprint Plan

### Week 1 (Parallel Tracks)

Track A — Business Foundation (you do this): - Day 1: File Delaware C-Corp via Stripe Atlas - Day 2: Apply for EIN on irs.gov - Day 2: Open Mercury business bank account - Day 2: Get insurance quotes (Hiscox + Coalition) - Day 3: Register domain (compoundiq.com), set up Google Workspace - Day 3: Send BAA request emails to all 6 vendors (template below)

Track B — Marketing Site (weekend project): - Day 6 (Saturday): Build 3-page Framer site - Day 7 (Sunday): Generate Privacy Policy + ToS via Termly, add to site

Track C — Outreach (from launch-kit/clinic-outreach-email): - Day 1-5: Email 5-8 warm clinic contacts (launch-kit/clinic-outreach-email.docx)

### Week 2

- LegitScript application submitted (using outputs from Week 1)

- Stripe Connect platform application submitted

- Twilio A2P 10DLC brand registration started

- Insurance policies in force

- Demo calls with clinics booked

### Week 3

- 1-2 design partner LOIs signed (launch-kit/design-partner-agreement.docx)

- Pharmacy outreach begins to their named pharmacies (launch-kit/pharmacy-outreach-email.docx)

- BAAs arriving — file each as it lands

- Documo production account provisioned

- Monitoring/alerting end-to-end test complete

### Week 4

- LegitScript reviewer questions answered (reply within 24h)

- Stripe Connect platform approved (optimistically)

- First pharmacy catalog loaded

- First test prescription run end-to-end with a design partner (may still be test-mode)

- Sentry + PagerDuty paging confirmed working

### Week 5-8 (Post-Launch Polish)

- LegitScript approved → seal embedded on marketing site

- Nice-to-haves from Bucket 4 as time permits

- First real production transaction with real patient + real money

- Case study interviews scheduled

## BAA Request Email Template

Paste this template, customize the vendor name, send to all 6 vendors in Week 1:

Subject: HIPAA BAA request — CompoundIQ Inc.

Hello [Vendor] team,

CompoundIQ Inc. is a B2B2C infrastructure platform connecting functional medicine clinics with compounding pharmacies. We currently use [Vendor] in our production stack and are preparing for launch with our first design partner clinics.

Protected Health Information (PHI) will flow through our application, and we are implementing HIPAA-adjacent controls throughout: AES-256 encryption at rest, TLS 1.2+ in transit, Row-Level Security on all database tables, zero-PHI in payment processor metadata, PHI-scrubbed error monitoring, and immutable audit trails.

To complete our compliance posture, we need a Business Associate Agreement with [Vendor]. Could you send your BAA template, confirm the required plan/tier, and let us know the typical turnaround time for execution?

Our account email is [YOUR EMAIL], and our incorporation details can be provided on request.

Thank you, [YOUR NAME] Founder, CompoundIQ Inc. [YOUR PROFESSIONAL EMAIL]

## Vendor Contact Directory

| Vendor | Purpose | Contact | BAA Request Sent | BAA Received | Notes |
| --- | --- | --- | --- | --- | --- |
| Supabase | Database + Auth | security@supabase.com |  |  | Team plan required |
| Stripe | Payments + Connect | Dashboard → HIPAA request |  |  | Platform + BAA |
| Twilio | SMS | Sales contact |  |  | Plus A2P registration |
| Documo | Fax | support@documo.com |  |  | Production tier |
| Vercel | Hosting | sales@vercel.com |  |  | Enterprise required — slowest |
| Sentry | Error monitoring | compliance@sentry.io |  |  | Business plan+ |
| Mercury | Banking | Not HIPAA-scoped | N/A | N/A | No BAA needed |

## Budget Summary

### One-Time Costs

| Item | Cost |
| --- | --- |
| Entity formation (Stripe Atlas) | $500 |
| LegitScript application | $975 |
| Twilio A2P 10DLC brand registration | $44 |
| Privacy Policy + ToS (Termly 1 yr) | $120 |
| Marketing site setup (Framer) | $0 (first month free) |
| Domain (compoundiq.com) | $12/yr |
| One-time total | ~$1,651 |

### Recurring Monthly Costs (post-BAAs, production tier)

| Item | Monthly |
| --- | --- |
| Supabase Team plan | $599 |
| Vercel Enterprise | TBD (contact sales) |
| Sentry Business | ~$80 |
| Twilio (base + campaign) | $10 + usage |
| Documo production | $30-$150 |
| Google Workspace | $6/user |
| Mercury banking | $0 |
| Framer site | $20 |
| Recurring total | ~$750-$900+/mo |

### Annual Costs

| Item | Annual |
| --- | --- |
| General liability insurance | $500-$1,500 |
| Cyber liability insurance | $1,500-$5,000 |
| LegitScript monitoring | $1,295 |
| Domain renewal | $12 |
| Annual total | ~$3,300-$7,800 |

### Runway Implications

At ~$900/mo recurring + $1,651 one-time + $3,300/yr annual = roughly $15-$20K for the first 12 months of pre-revenue infrastructure and compliance costs. Fits comfortably in either $250K or $500K angel round scenarios from the Investment Memo.

## Status Update Log

Add entries here weekly to track progress:

| Date | Items Completed This Week | Blockers | Next Week’s Focus |
| --- | --- | --- | --- |
| 2026-04-16 | Doc created | None yet | Entity, EIN, BAA emails |

## Open Questions to Decide

- ☐ Which entity formation service? (Stripe Atlas vs Clerky vs lawyer)

- ☐ Mercury vs Brex for banking?

- ☐ Framer vs Webflow vs custom Next.js marketing site?

- ☐ Domain name if compoundiq.com is taken — alternatives?

- ☐ Who is the emergency contact / on-call number for PagerDuty?

- ☐ Founder equity split (if co-founder involved)?

- ☐ Advisory pool size (0.5% or 1% total)?